Project Proposal

- Project Title:			CONNECT

- Project Proponent: 		JUAN DELA CRUX

- Time Frame:			Project Start: September 23, 2019

Project Ends: October 19, 2019

- Target Beneficiaries:		25 out of school youth (OSY)engaging inhalant

(Vulcazeal) and 25 household Parent

- Total Budgetary Requirements:	44,000.00 Pesos only

- Project Rationale:

The proponent has conducted a survey and gathered information in Purok Saludin, Barangay Labangal, General Santos City and as result, they found out that the community has a problem regarding the increasing number of out of school (OSY) engaging inhalant Vulcazeal and parents used their time in gambling. Hence, the connect project conceptualized with the help of the community to develop and be productive regarding on the problem by connecting and developing their strength. In order to resolve the problem, the proponent proposes to organize the out of out of school youth and parents into community volunteer to be a helping hand to achieved healthy community project. There will be series of training to be undertaken on the target client.

- Developmental Goal:

At the end of the project implementation, the community of Purok Saludin will have its well-trained community volunteers, and active and participative youth in promoting peace and development in the barangay.

- Project Description:

The Connect Project entails on the creation of community volunteers into promoting peace and development, healthy life style, personality development, drug awareness and importance of voluntarism for OSY’s and time management training for household parents.

- Project Component:

The Connect Project has the following components:

- Community volunteer training for youth

- Mobilizing youth in community project ( Feeding Activities)

- Time management Training for 25 households parents

- Recollection

- Project Objective:

The purpose of the project is to:

- To enable the youth to become active and participative in community activities

- To provide the parents with through training in time management and community engagement

- Implementation Scheme:

The implementation of this project is through organizing the youth and training for parents  by the ACM Group to the residence of Purok Saludin Barangay Labangal, General Santos City, after the said organization and , the group will be facilitated the training on peace and development, healthy lifestyle, personality development and drug awareness for target  OSY’s and time management training for target household parents for the purpose of achieving the participation of youth and parents manage their time well and engage in community activities.

- Project Feasibility:

The project will support the inhabitants’ interest and willingness to resolve their problem on increasing number of OSY’s inhaling vulcazeals; facilitate them to be more productive in their way of life, community and let them appreciate the value of time. Hence, its feasibility will be the availability of parents in youth during the said activities.

- Monitoring and Evaluation:

The proponent monitors and evaluate through follow up visitation and meetings, reports from the purok leaders, documentation and certificate.

- Project Sustainability:

The partner agencies, City Social Welfare and Development, Barangay Council and Purok council will ensure the functionality of organized group by continuing the plan of activities of youth.

- Detailed Budget Requirement:

- 2 day community volunteer training for youth

| particulars |  |  | Source of Funds |
| --- | --- | --- | --- |
| Honorarium | 1000x3 speakers | 3,000.00 | SK Fund |
| Certificate |  | 700.00 | SK Fund |
| Documentation |  | 700.00 | SK Fund |
| snacks | 30 pax. x 25/snacks x 4 snacks | 3,000.00 | SK Fund |
| meals | 30 pax. X 50 /meals x 4 meals | 6,000.00 | SK Fund |
| Tarpaulin | 2 pcs. X 200 (20x16) | 400.00 | SK Fund |
| facilitator | 6 Facilitatorx3daysx500 | 9,000.00 | Proponent |
| transportation |  | 1,000.00 | SK Fund |
| Total budget |  | 23,800,00 |  |

- Mobilizing youth in community project ( Feeding Activities and Child Friendly Spaces)

|  |  |  | Source of Funds |
| --- | --- | --- | --- |
| Lugaw | 100 children | 2,000.00 | Hon. Lagare |
| styro cups | 50/12 dozens/packsx11 packs | 550.00 | Hon. Lagare |
| Total Budget |  | 2,550.00 |  |

- 1 day time management training for household parents

|  |  |  | Source of Funds |
| --- | --- | --- | --- |
| Honorarium |  | 1,000.00 | BOBSLOR |
| Certificate |  | 300.00 | BOBSLOR |
| Documentation |  | 300.00 | BOBSLOR |
| snacks | 30 pax. x 25/snacks x 2 snacks | 1,500.00 | BOBSLOR |
| meals | 30 pax. x 50/meals x 1 meal | 1,500,00 | BOBSLOR |
| facilitator | 6 facilitator x500x 1/day | 3,000.00 | Proponent |
| Total Budget |  | 7,600.00 |  |

- Recollection

|  |  |  | Source of Funds |
| --- | --- | --- | --- |
| Honorarium | 1000x2 speakers | 2,000.00 | BOBSLOR |
| Certificate |  | 300.00 | BOBSLOR |
| Documentation |  | 300.00 | BOBSLOR |
| snacks | 30 pax. x 25/snacks x 2 snacks | 1,500.00 | BOBSLOR |
| meals | 30 pax. x 50/meals x 1 meal | 1,500,00 | Proponent |
| facilitator | 6 facilitator x500x 1/day | 3,000.00 | BOBSLOR |
| transportation |  | 1,000.00 | Brgy. Council |
| Venue |  | 3,000.00 | Brgy. Council |
| Total Budget |  | 12,600.00 |  |

Proponent:

Juan dela Crux

Recommending Approval:

Mainok N. Pula, RSW

Subject Teacher

Approved by:

HON. LORELIE PACQIAO

Punong Barangay

Barangay Labangal

General Santos City

Flow of Activities

2 days Community Volunteer Training for Youth

| Day/Date | Time | Activity | Responsible Person |
| --- | --- | --- | --- |
| Day 1 | 8:00-10:00 AM | Registration | Facilitator |
| October 1, 2013 | 10:00 -12:00 NN | Opening Invocation National Anthem Objective Presentation Self Introduction Groupings | Facilitator |
|  | 12:00 NN – 1:00 PM | Lunch | Facilitator, Participants |
|  | 1:00- 3:00 PM | Self -awareness | Speaker |
|  | 3:00-3:15 PM | Snacks | Facilitator, Participants |
|  | 3:15-5:00 Pm | Healthy living | Speaker |
|  | 5:00-7:00 Pm | Self preparation | Facilitator, Participants |
|  | 7:00 – 9:00 PM | Importance of Education | Speaker |
|  | 9:00 – 11:00 PM | Socio -cultural | Facilitator, Participants |
| Day 2 | 4:30 – 5:00 AM | Self Preparation | Facilitator, Participants |
| October 2, 2013 | 5:00 – 7:00 AM | Zumba | Facilitator, Participants |
|  | 7:00-8:00 AM | Breakfast | Facilitator, Participants |
|  | 8:00- | Drug Awareness |  |
|  |  | Symposium | Facilitator, Participants |
|  | 12:00 -1:00 PM | Lunch | Facilitator, Participants |
|  | 1:00-3:00 PM | Essence of Voluntarism |  |
|  | 3:00-3:15 PM | Snacks | Facilitator, Participants |
|  | 3:15-5:00 Pm | Closing Program Learning insight Distribution of Certificate Closing Remarks Closing Prayer | Facilitator, Participants, Invited Guest |
| HOME SWEET HOME |  |  |  |

Flow of Activities

Time management training for household parents

| Date | Time | Activity | Responsible Person |
| --- | --- | --- | --- |
| October 3, 2013 | 8:00-9:00 AM | Registration | Facilitator |
|  | 9:00 -12:00 NN | Opening Invocation National Anthem Objective Presentation Self Introduction Groupings | Facilitator |
|  |  | Importance of managing time | Speaker |
|  | 12:00 NN – 1:00 PM | Lunch | Facilitator, Participants |
|  | 1:00- 3:00 PM | Importance of managing time | Speaker |
|  |  | Creating Time Management Planner | Speaker |
|  | 3:00-3:15 PM | Snacks | Facilitator, Participants |
|  | 3:15-5:00 Pm | Closing Program Learning insight Distribution of Certificate Closing Remarks Closing Prayer | Facilitator, Participants, Invited Guest |
| HOME SWEET HOME |  |  |  |

Flow of Activities

Mobilizing youth in community project

(Feeding Activities and child friendly Spaces)

| Date | Time | Activity | Responsible Person |
| --- | --- | --- | --- |
| October 5, 2013 | 1:00-5:00 PM | Opening Invocation National Anthem Objective Presentation | Proponent, parents volunteer youth volunteer |
|  |  | Games and recreation | Proponent, parents volunteer youth volunteer |
|  |  | Feeding | Proponent, parents volunteer youth volunteer |

Flow of Activities

Recollection

| Date | Time | Activity | Responsible Person |
| --- | --- | --- | --- |
| October 4, 2013 | 8:00-9:00 AM | Registration | Facilitator |
|  | 9:00 -12:00 NN | Opening Invocation National Anthem Objective Presentation Self Introduction | Facilitator |
|  |  | Importance of Having Recollecting the past | Speaker |
|  | 12:00 NN – 1:00 PM | Lunch | Facilitator, Participants |
|  | 1:00- 3:00 PM | Recollection of past | Speaker |
|  |  | Reflection | Speaker |
|  | 3:00-3:15 PM | Snacks | Facilitator, Participants |
|  | 3:15-5:00 Pm | Closing Program Distribution of Certificate Closing Remarks Closing Prayer | Facilitator, Participants, Invited Guest |
| HOME SWEET HOME |  |  |  |

Action Plan

| ACTIVITIES | Month |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | September |  |  |  | October |  |  |  |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| - Present the plan to Purok Officers |  | x |  |  |  |  |  |  |
| - Identify venue for the training |  | x |  |  |  |  |  |  |
| - Send invitation letter to participants |  | x |  |  |  |  |  |  |
| - Conducted time management training to target household parents |  |  | x |  |  |  |  |  |
| - Organize the target youth |  |  | x |  |  |  |  |  |
| - Conduct training for organized youth |  |  |  | x |  |  |  |  |
| - Filling of training and activity documents |  |  |  | x |  |  |  |  |
| - Monitoring and evaluation |  |  |  |  | x |  |  |  |
| - Finalizing the documents |  |  |  |  | x |  |  |  |
| - Termination |  |  |  |  |  | x |  |  |